Course Registration and Timetable Scheduler

Software Construction Project

Group Members:

Aftab Shaban

04072312046

Submitted to: Dr. Umar Rashid

Table of Contents

Part I: Project Planning Phase	5

P1. Project Overview	5

P1.1 Background and Problem Statement	5

P1.2 Project Objectives	5

P1.3 Project Scope	5

P1.4 Project Deliverables	6

P1.5 Assumptions, Dependencies and Constraints	6

P2. Feasibility Study	6

P3. Project Organisation	7

P3.1 Process Model	7

P3.2 Stakeholders	7

P3.3 Team Roles and Responsibilities	7

P3.4 Communication and Reporting	8

P4. Managerial Process Plan	8

P4.1 Work Breakdown Structure and Effort	8

P4.2 Schedule and Milestones	9

P4.3 Resource Plan	10

P5. Risk Management Plan	10

P6. Technical and Supporting Processes	11

P6.1 Methods, Standards and Tools	11

P6.2 Quality Assurance and Verification Plan	11

P6.3 Configuration Management	11

P6.4 Requirements Change Control	11

P6.5 Acceptance Criteria for the Release	12

Part II: Requirements Analysis Phase (Software Requirements Specification)	13

1. Introduction	13

1.1 Purpose	13

1.2 Document Conventions	13

1.3 Product Scope	13

1.4 Definitions, Acronyms and References	13

2. Overall Description	13

2.1 Product Perspective	13

2.2 Product Functions	14

2.3 User Classes and Characteristics	14

2.4 Operating Environment	14

2.5 Design and Implementation Constraints	15

2.6 User Documentation	15

2.7 Assumptions and Dependencies	15

2.8 Future Enhancements (Apportioning of Requirements)	15

3. External Interface Requirements	15

3.1 User Interfaces	15

3.2 Hardware Interfaces	16

3.3 Software Interfaces	16

3.4 Communications Interfaces	16

# Part I: Project Planning Phase

This part is the project management plan for the Course Registration and Timetable Scheduler (CRTS). It explains what we are building, why, who is building it, when it will be done, and how we will keep risk and quality under control. It follows IEEE Std 1058-1998. Part II picks up from here with the detailed requirements.

## P1. Project Overview

### P1.1 Background and Problem Statement

Right now, course registration at the university is done by hand. Students fill in forms, staff check seat availability and timetable clashes themselves, and records sit in separate lists. This is slow and error-prone. Classes end up over-enrolled, clashes go unnoticed, student records drift out of sync, and staff lose a lot of time at the start of every semester.

### P1.2 Project Objectives

Table 1: Project objectives and success measures

| ID | Objective | Measure of success |
| --- | --- | --- |
| O1 | Let students register for and drop courses online through a desktop application. | All 8 core use cases (UC1–UC8) pass system tests. |
| O2 | Prevent invalid registrations automatically (prerequisites, seat capacity, credit limit, time clash). | 0 invalid registrations accepted in acceptance testing. |
| O3 | Generate a conflict-free weekly timetable for a student. | Timetable produced in 3 seconds or less (NFR-3). |
| O4 | Give administrators central control of courses, sections and student accounts. | Admin can complete add, edit, archive and import tasks without database access. |
| O5 | Provide registration, occupancy and timetable reports. | Reports export to PDF and Excel. |
| O6 | Protect data and access with role-based security. | Passwords stored as salted hashes; no SQL-injection findings in security review. |
| O7 | Deliver within one semester with the planned effort. | All milestones M1–M5 met; actual effort within 15% of the 462-hour baseline. |

### P1.3 Project Scope

In scope

Secure login and logout for students and administrators with role-based dashboards.

Administrator management of courses, sections (capacity, instructor, room, weekly time slots), prerequisites and student accounts.

Student registration and dropping of course sections with automatic validation.

Timetable generation, clash detection and grid display of a student's weekly timetable.

Registration, occupancy and timetable reports with PDF and Excel export.

Database design and scripts (MySQL 8.0), in-app help and a PDF user manual.

Out of scope for this release

Web or mobile clients (a REST API is a future option only).

Fee payment, refunds, grading, transcripts and instructor portals.

Two-factor or biometric authentication and e-mail notifications.

University-wide timetable optimisation (room and instructor allocation). CRTS only checks and shows the time slots that administrators set for each section.

### P1.4 Project Deliverables

Table 2: Deliverables

| # | Deliverable | Phase | Due |
| --- | --- | --- | --- |
| D1 | Project Management Plan (Part I of this document) | Planning | M1 (W2) |
| D2 | Software Requirements Specification (Part II), use case model, SSDs, domain model | Analysis | M2 (W4) |
| D3 | Architecture, database schema (ERD + DDL), class and sequence design, UI prototypes | Design | M3 (W6) |
| D4 | Source code (Java Swing application), SQL install and seed scripts | Implementation | M4 (W11) |
| D5 | Test plan, test cases and test report | Testing | M4–M5 |
| D6 | PDF user manual and in-app help | Deployment | M5 (W14) |
| D7 | Final release package and presentation | Deployment | M5 (W14) |

### P1.5 Assumptions, Dependencies and Constraints

Constraint: the product has to use Java Swing for the interface and MySQL for the database, and follow the MVC pattern.

Constraint: the project has to follow the university guidelines for the CS322 Software Construction course.

Constraint: the team is fixed at two members and the semester is fixed at 14 weeks.

Assumption: a MySQL 8.0 server is available on every development machine and in the demo environment.

Assumption: the supervisor and some sample users (one administrator and a few students) are available for reviews and acceptance testing.

Dependency: the university provides the drop deadlines, credit-hour limits and a sample course catalogue (see Part II, Appendix C).

## P2. Feasibility Study

Before starting the requirements work, we looked at feasibility from five angles.

Table 3: Feasibility assessment

| Dimension | Assessment | Verdict |
| --- | --- | --- |
| Technical | Java Swing, JDBC and MySQL are mature, well documented and already part of the course. No new technology is needed. Clash detection reduces to interval-overlap checks on (day, start, end), and seat control to transactional updates. | Feasible |
| Economic | All tools are free or open source (see P4.3), so there are no licence costs. The only cost is team effort of about 462 person-hours. Benefits are less manual work, fewer errors and centralised data. | Feasible |
| Operational | Users are administrators and students with basic computer skills. The desktop application runs on standard Windows machines and follows familiar form-and-table patterns. A user manual and in-app help support adoption. | Feasible |
| Schedule | 462 hours over 14 weeks is about 16.5 hours per member per week. This is achievable with three increments, a prioritised scope (High requirements first) and a 15% reserve. | Feasible with risk (see R5) |
| Legal and ethical | The system stores student personal data. It must follow the university data policy, store passwords only as hashes, restrict access by role and log administrative changes. | Feasible |

Conclusion: the project is feasible within our constraints, so we can move on to requirements analysis.

## P3. Project Organisation

### P3.1 Process Model

The project follows an iterative-incremental model. Planning, requirements and design are done up front, because the registration rules are stable and well understood. Implementation is then delivered in three increments, each ending in a tested build we can demonstrate: Increment 1 (login and course management), Increment 2 (registration and drop) and Increment 3 (timetable generation and reports). This way the supervisor sees progress early and late changes cost less.

### P3.2 Stakeholders

Table 4: Stakeholders

| Stakeholder | Role in the project | Main interest |
| --- | --- | --- |
| Students | End users of registration and timetable functions | Fast, conflict-free registration; clear timetable |
| Administrators / registrar staff | End users; maintain courses, sections and accounts | Accurate catalogue, less manual work, reliable reports |
| Course supervisor / reviewer | Reviews and approves deliverables at milestones | Compliance with course guidelines, traceability, quality |
| University | Owner of rules and data (credit limits, deadlines) | Accurate enrolment records, policy compliance |
| Development team | Muzaffar Ali and Aftab Shaban | On-time delivery of a working, well-documented product |

### P3.3 Team Roles and Responsibilities

Table 5: Roles

| Role | Responsibilities |
| --- | --- |
| Project manager | Plan, schedule, status reporting, risk register, change control |
| Requirements analyst | Elicitation, SRS, use cases, domain model, traceability |
| Designer / architect | Architecture, database schema, class and sequence design, UI prototypes |
| Developer | Implementation of modules, unit tests, code reviews |
| Tester / QA | Test plan, test cases, system and acceptance testing, defect tracking |
| Configuration manager | Repository, baselines, build and release packages |

### P3.4 Communication and Reporting

A 30-minute team meeting every week to go over progress, risks and decisions.

A review with the supervisor at each milestone (M1 to M5). Comments are logged and followed up until they are closed.

A shared Git repository holds the code, documents and SQL scripts, and a task board tracks the work packages from the WBS.

Decisions and requirement clarifications are recorded in the open-issues list (Part II, Appendix C).

## P4. Managerial Process Plan

### P4.1 Work Breakdown Structure and Effort

The work is split into six main packages. Effort is the team's own bottom-up estimate in person-hours.

Table 6: Work breakdown structure with effort estimate

| WBS | Work package | Effort (h) |
| --- | --- | --- |
| 1 | Project Management | 44 |
| 1.1 | Project planning, feasibility study, plan baseline | 16 |
| 1.2 | Monitoring, weekly status meetings, reporting | 20 |
| 1.3 | Risk management and change control | 8 |
| 2 | Requirements Analysis | 74 |
| 2.1 | Elicitation and stakeholder analysis | 12 |
| 2.2 | SRS authoring (IEEE 830 / 29148 structure) | 24 |
| 2.3 | Use case modelling and system sequence diagrams | 20 |
| 2.4 | Domain model and data dictionary | 10 |
| 2.5 | SRS inspection and baseline | 8 |
| 3 | Design | 48 |
| 3.1 | Architecture (two-tier, MVC) | 8 |
| 3.2 | Database schema (ERD, DDL scripts) | 12 |
| 3.3 | Class and sequence design | 14 |
| 3.4 | UI prototypes (Login, Admin Dashboard, Student Panel) | 14 |
| 4 | Implementation | 168 |
| 4.1 | Database creation and DAO layer (JDBC) | 24 |
| 4.2 | Authentication and account management | 16 |
| 4.3 | Course, section and prerequisite management | 24 |
| 4.4 | Registration and drop module | 32 |
| 4.5 | Timetable generation and clash detection | 28 |
| 4.6 | Reports and export (PDF / Excel) | 20 |
| 4.7 | UI integration and validation | 24 |
| 5 | Testing | 92 |
| 5.1 | Test plan and test case design | 14 |
| 5.2 | Unit testing (JUnit) | 24 |
| 5.3 | Integration and system testing | 24 |
| 5.4 | User acceptance testing | 10 |
| 5.5 | Defect fixing and regression | 20 |
| 6 | Deployment and Documentation | 36 |
| 6.1 | PDF user manual | 14 |
| 6.2 | In-app help | 6 |
| 6.3 | Packaging, DB install script, backup script | 8 |
| 6.4 | Final presentation and handover | 8 |
|  | Total baseline effort | 462 |

We keep a 15% management reserve (about 69 hours) outside the baseline for rework and risk response.

### P4.2 Schedule and Milestones

Figure 1: Baseline project schedule (weeks W1 to W14, milestones M1 to M5)

Table 7: Milestones

| Milestone | Week | Exit criterion |
| --- | --- | --- |
| M1: Plan approved | W2 | Project plan, feasibility and risk register reviewed by the supervisor |
| M2: Requirements baseline | W4 | SRS inspected; no open critical defects; traceability matrix complete |
| M3: Design review | W6 | Architecture, ERD, class design and UI prototypes approved |
| M4: Feature complete | W11 | Increments 1–3 integrated; all High-priority requirements implemented |
| M5: Release | W14 | System and acceptance tests passed; manual delivered; final presentation |

### P4.3 Resource Plan

Table 8: Tools and resources

| Resource | Use |
| --- | --- |
| Java JDK 17+, Eclipse IDE | Development of the Swing application |
| MySQL 8.0 server and MySQL Workbench | Database, schema design, test data |
| mysql-connector-j 9.5.0 (JDBC) | Database access |
| JUnit 5 | Unit tests of business logic (clash detection, credit limit, seat control) |
| Git and a hosted repository | Version control, baselines, backup of work |
| UML tool (for example draw.io or StarUML) | Use case, sequence, domain and class diagrams |
| Two development computers (4 GB RAM minimum, 8 GB recommended) | Development and testing, Windows 10 or later |

## P5. Risk Management Plan

We identify risks while planning and review them at each weekly meeting. Probability (P) and impact (I) are rated from 1 (low) to 5 (high), and exposure is P × I. Any risk with an exposure of 12 or more gets a named owner and a contingency plan.

Table 9: Risk register

| ID | Risk | P | I | Exp. | Mitigation / contingency |
| --- | --- | --- | --- | --- | --- |
| R1 | Scope creep (web or mobile clients, extra features) | 4 | 3 | 12 | Baseline the SRS; process every change through P6.4; park extras in the future-enhancements list. |
| R2 | Clash-detection edge cases (several slots per section, back-to-back classes) | 3 | 4 | 12 | Prototype the algorithm in Increment 2; unit tests with boundary cases. |
| R3 | Two students registering for the last seat at the same time | 3 | 4 | 12 | Check and update seats in one transaction with row locking; concurrency test. |
| R4 | Team member unavailable (illness, exams) | 2 | 4 | 8 | Backup owner per role; documentation kept current; reserve hours. |
| R5 | Implementation slips past W11 | 3 | 3 | 9 | Deliver High-priority requirements first; defer Low-priority ones (CSV import, printing). |
| R6 | JDBC or MySQL set-up problems on different machines | 2 | 3 | 6 | Scripted install; setup instructions in the manual; same versions on all machines. |
| R7 | Ambiguous or inconsistent requirements | 3 | 3 | 9 | Formal SRS inspection at M2; open-issues log with decisions. |
| R8 | Data loss or corruption | 2 | 5 | 10 | Daily backup (NFR-6), transactions, restore test before release. |
| R9 | Security weakness (SQL injection, weak password storage) | 2 | 5 | 10 | Prepared statements only; salted hashing; security checklist in code review. |
| R10 | Poor usability | 2 | 3 | 6 | UI prototypes at M3; trial with sample users during UAT. |
| R11 | Performance below target with 200 concurrent users | 2 | 3 | 6 | Index key columns; connection pooling; load test in system testing. |

## P6. Technical and Supporting Processes

### P6.1 Methods, Standards and Tools

Requirements: we use the IEEE Std 830-1998 structure, with the requirement attributes from ISO/IEC/IEEE 29148 (ID, priority, source, verification).

Modelling: UML 2 for use case, sequence, domain and class diagrams; use cases are written in the fully dressed format.

Coding: Java 17 with MVC and a DAO layer, CamelCase names for variables, classes and methods, and Javadoc on public methods.

Database: MySQL 8.0 with lower-case snake_case table and column names; foreign keys and unique constraints are defined in the DDL scripts.

### P6.2 Quality Assurance and Verification Plan

Quality is built in through reviews and checked by testing at four levels. A teammate inspects each document, following the walkthrough and inspection practice of IEEE Std 1028.

Table 10: Test levels

| Level | Scope | Entry criterion | Exit criterion |
| --- | --- | --- | --- |
| Unit | Business rules: clash detection, credit limit, seat control, password hashing, validation | Module coded and compiled | All unit tests pass; business logic coverage of 80% or more |
| Integration | Controller to DAO to database for each use case | Unit tests pass | No open critical or high defects in the increment |
| System | All use cases and non-functional requirements (performance, security) | M4 build | Every High requirement verified; traceability matrix complete |
| Acceptance (UAT) | Scenarios run by the supervisor and sample users | System tests passed | Supervisor sign-off |

Defect severity: Critical means data loss, a security breach or an unusable system. High means a use case cannot be completed. Medium means there is a workaround. Low means cosmetic. We do not release with any open Critical or High defects.

### P6.3 Configuration Management

One Git repository with a main branch for released baselines and a develop branch, plus one feature branch per work package.

Baselines are tagged: SRS v1.3 at M2, the design baseline at M3, v0.1 to v0.3 for each increment and v1.0 at M5.

SQL schema and seed scripts are versioned with the code. Every document carries a version number and a revision history.

Commit messages name the work package or requirement ID, for example “FR-24: check seat availability”.

### P6.4 Requirements Change Control

Anyone can raise a change request, stating what the change is, why it is needed and which requirement IDs it affects.

The team assesses the impact on scope, effort, schedule, risk and tests. Changes costing more than 8 hours need the supervisor's approval.

Approved changes update the SRS version, the traceability matrix and this plan. Rejected requests are logged with the reason.

### P6.5 Acceptance Criteria for the Release

All High-priority functional requirements are implemented and pass system tests. Medium requirements are either implemented or formally deferred.

The non-functional targets in Part II, Section 9 are met, or any exceptions are approved.

No Critical or High defects are open, and the user manual, in-app help, database install script and backup script are delivered.

# Part II: Requirements Analysis Phase (Software Requirements Specification)

This part is the Software Requirements Specification (SRS) for the Course Registration and Timetable Scheduler (CRTS). It follows the section structure of IEEE Std 830-1998 and adds the requirement attributes from ISO/IEC/IEEE 29148:2018 (unique ID, priority, source and verification method). It is the baseline for design, implementation and testing.

## 1. Introduction

### 1.1 Purpose

This document sets out what the Course Registration and Timetable Scheduler must do. The system lets students register for courses and builds clash-free timetables for them automatically. It is written for developers, testers and supervisors, and it is the baseline for design, implementation and verification.

### 1.2 Document Conventions

The structure follows IEEE Std 830-1998. That standard has been replaced by ISO/IEC/IEEE 29148:2018, so we also use its requirement attributes.

Identifiers: FR-n is a functional requirement, NFR-n a non-functional requirement, BR-n a business rule, UCn a use case and A-n an assumption.

“Must” marks a mandatory requirement and “should” a recommendation. Anything not yet decided is marked TBD and listed in Appendix C.

Priority: High (must have; the release fails without it), Medium (should have), Low (nice to have; the first to be deferred).

Verification method: T = test, D = demonstration, I = inspection, A = analysis.

CamelCase is used for variables, classes and methods in models and code.

### 1.3 Product Scope

CRTS lets students register for classes online and lets administrators manage course data and check for scheduling problems. The system keeps data consistent, validates the rules and builds timetables automatically. The main benefits are central course data, fewer human errors and less work for staff. The objectives, scope and exclusions are in Part I (P1.2 and P1.3).

### 1.4 Definitions, Acronyms and References

Terms and abbreviations are explained in Appendix A, and the documents we refer to are listed in Appendix B.

## 2. Overall Description

### 2.1 Product Perspective

CRTS is a new, self-contained desktop application with two tiers. The client tier is written in Java Swing and holds the user interface and the application logic (MVC). The data tier is a MySQL database that the client reaches through JDBC. It replaces the manual registration process and does not connect to any other university system in this release.

Figure 2: System context and two-tier architecture of CRTS

### 2.2 Product Functions

Table 11: Product functions

| Function group | Summary | Users |
| --- | --- | --- |
| Authentication | Secure login and logout, role-based dashboards, session timeout, account lock | Student, Administrator |
| Account management | Create, edit, deactivate student accounts; reset passwords | Administrator |
| Course management | Maintain courses, sections, time slots, capacities and prerequisites; CSV import | Administrator |
| Registration | View available sections, register and drop with automatic checks of prerequisites, seats, credit limit and clashes | Student |
| Timetable | Generate a conflict-free timetable, view it in a grid, print or export it | Administrator, Student |
| Reports | Registration summary, course occupancy and timetable statistics with PDF and Excel export | Administrator |

### 2.3 User Classes and Characteristics

Table 12: User classes

| User class | Description | Privileges | Expertise |
| --- | --- | --- | --- |
| Student | Registers, drops, views the timetable and account information. Uses the system mostly at registration time. | Own registrations and timetable only; read-only course catalogue | Basic computer skills |
| Administrator | Manages courses, sections, student accounts and timetables; generates reports. Uses the system throughout the semester. | All administrative functions; no access to other users' passwords | Knowledge of academic scheduling |

### 2.4 Operating Environment

Operating system: Windows 10 or later is the main target. Since the application is built in Java it should also run on Linux and macOS, but we do not formally test those in this release.

Software: Java JDK 17 or later and MySQL 8.0, developed in the Eclipse IDE.

Hardware (minimum): 4 GB RAM, 1 GHz CPU and a 1024 × 768 display; 8 GB RAM is recommended for the database server.

Network: the database runs on the same machine or on a local network the client can reach.

### 2.5 Design and Implementation Constraints

The interface must be built in Java Swing and the data stored in MySQL (course requirement).

The architecture must follow the MVC pattern, with database access kept in a DAO layer.

All SQL must use prepared statements (NFR-11).

The project must follow the university guidelines for the course and the schedule in Part I.

### 2.6 User Documentation

In-app help menu.

A PDF user manual with instructions and screenshots, with separate guides for students and administrators.

### 2.7 Assumptions and Dependencies

Table 13: Assumptions and dependencies

| ID | Assumption or dependency |
| --- | --- |
| A-1 | The MySQL server is installed, running and reachable (locally or on the LAN) whenever the application is used. |
| A-2 | Every student has a unique registration number issued by the university. |
| A-3 | Administrators define the weekly time slots of every section; CRTS does not allocate rooms or instructors. |
| A-4 | The university provides the credit-hour limits, the drop deadline and the registration period (see Appendix C, TBD-1 to TBD-3). |
| A-5 | Course prerequisites are course-level (a required course must be completed beforehand); the system holds each student's completed courses (TBD-4). |
| A-6 | One application instance is used per user at a time; many instances may use the same database. |

### 2.8 Future Enhancements (Apportioning of Requirements)

These items came up in version 1.2 but are not requirements for this release. We note them here so the design does not rule them out later.

Web or mobile access. Version 1.2 mentioned it in UC5 and UC7, but this is a desktop application. An optional REST API may be added later.

Two-factor or biometric authentication.

Automatic suggestion of alternate courses, student timetable preferences, scheduled report e-mails and fee or refund handling.

## 3. External Interface Requirements

### 3.1 User Interfaces

All screens share one look and keep buttons in consistent places. Every screen has a menu bar, a help entry and a status bar.

Table 14: Main screens

| Screen | Users | Main elements | Use cases |
| --- | --- | --- | --- |
| Login window | All | Username, password, role selection, Login button, error message area | UC1 |
| Admin Dashboard | Administrator | Buttons for course management, student accounts, timetable generation, reports; logout | UC2, UC3, UC6, UC8, UC9 |
| Student Panel | Student | Tabs for registration, registered courses and drop, timetable view, account information; logout | UC2, UC4, UC5, UC7 |
| Course and section form | Administrator | Course fields, section list, time-slot editor, prerequisite selector, CSV import | UC3 |
| Report window | Administrator | Report type and filters, preview table or chart, PDF/Excel export | UC8 |

Interface standards:

Mandatory fields are marked, and invalid input is explained in plain language next to the field.

Destructive actions (delete, drop) ask for confirmation (NFR-8).

Screens can be used with the keyboard (tab order, Enter to submit) and work at 1024 × 768 or larger.

The interface is in English. Dates use DD-MMM-YYYY and times use the 24-hour clock.

### 3.2 Hardware Interfaces

Standard desktop or laptop computer with keyboard, mouse and display.

An optional printer for timetable printouts, through the operating system's print service.

### 3.3 Software Interfaces

Table 15: Software interfaces

| Item | Specification |
| --- | --- |
| Database | MySQL 8.0 |
| Connector | JDBC driver mysql-connector-j 9.5.0, accessed through java.sql |
| Operating system | Windows 10 or later (primary); Linux and macOS (not formally tested) |
| Libraries | Java Swing, AWT, java.sql; a PDF and an Excel export library (to be chosen in design) |

### 3.4 Communications Interfaces

The client talks to MySQL over TCP/IP (default port 3306) through JDBC.

If the database is on a different machine, the connection must use TLS and a dedicated database account with only the privileges it needs (NFR-12).

There is no other network communication in this release.